## Slide 1: End‑to‑End Sunny Delivery Roadmap
2026
Preliminary

## Slide 2: End‑to‑End Sunny Delivery Roadmap
Phase 1: Foundation and Environment Setup
Phase 2: AI and Voice Integration
Phase 3: Lip Sync and Engine
Week 1, 2
Week 3
Week 4
Finalize Avatar Assets
Establish Google Cloud Foundation
Define High‑Level Architecture
GCP backend skeleton live
Animation‑ready avatar assets
Phase
Deliverable
Key
Activities
Integrate Vertex AI (Gemini)1 for response generation
Configure prompt framework
Integrate text‑to‑speech for audio generation
End‑to‑end pipeline generating spoken responses from user input
Integrate Rhubarb2 Lip Sync into containerized backend
Process audio output into viseme3 timing data
Extend APIs to return synced audio and viseme signals
Backend capable of producing synchronized speech and animation data
Phase 4: Frontend Avatar Rendering
Phase 5: Polish, Demo Readiness and Performance
Week 5, 6
Week 7, 8
Build React/Next.js4 talking‑head component
Implement audio playback and real‑time viseme‑driven mouth animation
Add animation smoothing for natural movement
Fully functional talking‑avatar interface
Add idle behaviors (blinking, subtle head motion)
Improve perceived latency Optimize Cloud Run performance and reduce cold starts
Conduct performance testing
Polished, demo‑ready talking avatar
EXECUTIVE DEMO
Governance & Controls (Run in Parallel)
Technology development will proceed alongside NIRA, TSR, and AI Council reviews to ensure risk alignment, delivery confidence, and readiness to scale.
Vertex AI is a fully-managed, unified AI development platform for building and using generative AI
Rhubarb Lip Sync is a free and open-source tool that automatically creates 2D mouth animation from voice recordings
Visemes are the visual, mouth-shape counterparts to phonetic sounds (phonemes) used to synchronize 2D/3D character animation with audio
UI and open-source full-stack web development framework